## Cross-Check Findings
# | Severity | Category | SoCal CList row(s) | Log tab / row(s) | Set / Dispatch ID | Issue | Suggested fix
1 | High | Missing from log | 520 | — | ID#420 (2/6 CEMEX) | Dispatched 4 cylinders, checklist marked Completed + Logged In, but no ID#420 set exists anywhere in the Whittier Cylinder Log. | Add the set to the Cylinder Log or correct the checklist's Concrete Log status.
2 | High | Missing from log | 552 | — | ID#408 (2/10 JPCP) | 6 cylinders + 3 beams dispatched, marked Logged In, but ID#408 appears in neither the Cylinder Log nor the Beam Log (ID#407 on 2/9 and ID#409 on 2/11 are both there). | Add cylinder and beam sets for ID#408 or correct the checklist.
3 | High | Missing from log | 2048 | — | ID#604 (5/7 Gardena) | 4 cylinders dispatched, marked Logged In, but no ID#604 set in the Cylinder Log. | Add the set or correct the checklist.
4 | High | Missing from log | 2927 | — | ID#765 (7/1 Gardena) | 4 cylinders dispatched, status Completed (Concrete Log cell left blank), no ID#765 set in the Cylinder Log. | Log the set; the blank Concrete Log cell suggests it was known to be un-logged.
5 | High | Missing from log | 3052 | — | ID#786 (7/8 Gardena) | 4 cylinders dispatched, marked Logged In, but no ID#786 set in the Cylinder Log (only ID#782 JPCP was cast/logged 7/8). | Add the set or correct the checklist.
6 | High | Wrong set name in log | 1985 | Cyl Log 2011 | ID#493 vs ID#495 | The 3/21 cast (26-0321-1_105_FC) was dispatch ID#493 (RW/SNW270) but was logged as '032026-ID495-CIDH-SW1433-1405-001' — an exact duplicate of the 3/20 ID#495 set. The 5/2 42-day break on checklist row 1985 therefore matches nothing. | Rename the 3/21 log rows to 032126-ID493-RWSNW270-001.
7 | High | Wrong ID in log | 3163 | Cyl Log 2263+ | ID571 should be ID671 | Log set '060326-ID571-SanPedro-LBSC-1' — dispatch on 6/3 was ID#671 (SanPedro LBSC); ID#571 is unrelated. Checklist break row 3163 (7/15) correctly uses ID671 and doesn't match the log. | Correct the log set name to ID671.
8 | High | ID conflict | 2494 | Cyl Log 2113/2118 | ID547 vs ID574 (4/21 SW1201) | The 4/21 SW1201 pour was dispatch ID#574. The log's 42-day row says ID574 but its 90-day row says ID547, and checklist break row 2494 (6/2) also says ID547. ID#547 was the separate 4/17 SW1201 field set. | Make all rows for the 4/21 set ID574.
9 | High | ID conflict | 2561, 2401 | Cyl Log 2255 | ID#636 vs ID#663 (5/29 LCB) | Both ID#636 and ID#663 were LCB dispatches on 5/29; only one set (ID663) exists in the log, yet checklist row 2401 marks ID#636 Completed + Logged In and break row 2561 references 052926-ID636. | Confirm whether one or two LCB pours happened 5/29; log the missing set or fix the references.
10 | High | WB/EB conflict | 3033, 3061 | Beam Log 286-287 | ID#752 / ID#753 JPCP beams | Cylinder Log and checklist name these pours 105WBJPCP; the Beam Log names the same pours 105EBJPCP. | Pick the correct roadway side (WB per cylinder log + checklist) and align the Beam Log.
11 | High | Bad dates in log | — | Cyl Log 5-6 | 012726-SW1202 / 012726-Avalon4L | Cast Date column contains a time (11:30) instead of the date, so the 56-day Break Date computes to 1900-02-25. | Enter cast date 1/27/26; break date becomes ~3/24/26.
12 | Med | Qty conflict | 1499 | Cyl Log 1886 | 022426-ID443 (42-day) | Checklist says Break 3 cylinders; log set quantity is 2. (JPCP dispatch spec was 3 @ 42-day.) | Verify actual cylinders broken; fix whichever is wrong.
13 | Med | Qty conflict | 1569 | Cyl Log 1904 | 022626-ID445 (42-day) | Checklist 3 vs log 2 (JPCP spec was 3). | Verify and fix.
14 | Med | Qty conflict | 1620-1622 | Cyl Log 1917-1919 | 030326-ID460 / ID451 / ID447 | Checklist 3 vs log 2 on all three 4/14 42-day breaks. | Verify and fix.
15 | Med | Qty conflict | 1643 | Cyl Log 1925 | 030426-ID452 | Checklist 3 vs log 2 (4/15). | Verify and fix.
16 | Med | Qty conflict | 1784-1785 | Cyl Log 1959-1960 | 031226-ID480 / ID466 | Checklist 3 vs log 2 (4/23). | Verify and fix.
17 | Med | Qty conflict | 3484-3485 | Cyl Log 2326-2327 | 062326-ID741 / ID730 | Checklist 3 vs log 2 (8/4, scheduled). | Verify and fix.
18 | Med | Qty conflict | 3207 | Cyl Log 2274 | 060426-ID653 (42-day) | Checklist 3 vs log 2 (7/17). | Verify and fix.
19 | Med | Qty conflict | 3162 | Cyl Log 2264 | 060326-ID672 (42-day) | Checklist 2 vs log 3 (7/15). | Verify and fix.
20 | Med | Qty conflict | 2182 | Cyl Log 2051 | 040226-ID514-JPCP105EB (42-day) | Checklist 2 vs log 3 (5/15). | Verify and fix.
21 | Med | Qty conflict | 540 | Cyl Log 1704 | S#6_Mix#25153CM (2/9 hold) | Checklist Break 3 vs log 2. | Verify and fix.
22 | Med | Qty conflict | 732 | Cyl Log 1724 | S#3_Mix#CT675F25 (2/24 hold) | Checklist Break 3 vs log 2. | Verify and fix.
23 | Med | Qty conflict | 2059 | Cyl Log 2138 | 042726-ID595 field pickup (10-day) | Checklist Break 4 vs log 2. | Verify and fix.
24 | Med | Qty conflict | 2220 | Cyl Log 2175 | 050826-ID608 field cure (10-day) | Checklist Break 4 vs log 2. | Verify and fix.
25 | Med | Year typo on checklist | 671 | Cyl Log 1709 | 010825-MSB-001 | Set cast 1/8/2026 — checklist wrote -25; log correctly has 010826. | Fix checklist to 010826-MSB-001.
26 | Med | Year typo on checklist | 687-688 | Cyl Log 1711-1712 | 010925-Avalon-001 / 010925-DS37C-001 | Cast 1/9/2026 — checklist wrote -25; log has 010926. | Fix checklist to 010926-…
27 | Med | Year typo in log | — | Beam Log 262-263 + Cyl Log | 010625-WB105-001 / 010725-WB105-001 | Cast 1/6-1/7/2026 but named with -25 year suffix in both logs. | Rename to 010626/010726-WB105-001.
28 | Med | Set-name typo | 468 | Cyl Log 1701 | 122325-RW282-001 vs 122325-SW282-001 | Checklist says RW282 (matching the RW282 structure); log says SW282. | Confirm structure; align both tabs.
29 | Med | Date-prefix typo (both tabs) | 1688 | Cyl Log 1932/1935 | ID#473 DS24H | Pour was cast 3/6 (BreakLog 26-0306-1). Log named the set 022726-ID473, checklist named it 030326-ID473 — neither matches the cast date (should be 030626). | Rename set to 030626-ID473-DS24H-001 in both tabs.
30 | Med | Duplicate set label | 3423-3424 | Cyl Log 2318-2319 | S#4_Mix#2102-OPT1 listed twice (8/1) | Both checklist rows say S#4, but the 6/20 D8 cast breaking 8/1 is S#5 and S#6 in the log. | Relabel the two checklist rows S#5 and S#6.
31 | Med | Set label conflict | 358 | Cyl Log 1685 | S#3 vs S#1 (CT675F25, 1/29 hold) | Checklist hold row says S#3; the log row breaking that day is S#1_Mix#CT675F25. | Verify which set was held/broken.
32 | Med | Set label conflict | 640, 897 | Cyl Log 1757/1760 | S#6_Mix#CT675F25 vs S#12_Mix#25153CM | Checklist 28-day (2/17) and 42-day-hold (3/3) rows cite S#6 CT675F25, but the 1/20 cast rows in the log are S#12 Mix 25153CM only — no S#6 CT675F25 set logged for those dates. | Verify the 1/20 D8 cast; add/rename as needed.
33 | Med | Wrong break description | 1405 | Cyl Log 1872/1874 | S#10_Mix#CT675F25 (2/25) | Checklist row says 'Break 2 @ 42-Days (HOLD)' on 2/25, but 2/25 was S#10's 7-day break; its 42-day (4/1) is marked HOLD in the log and never appeared on the checklist. | Change description to 7-Days; 42-day hold handled per log.
34 | Med | Set reference conflict | 2938 | Cyl Log 2217-2218 | 052026-ID521 vs ID621 (SW1420) | ID#521 was an unrelated 4/3 dispatch; the 5/20 SW1420 pour was ID#621 (log correct). | Fix checklist to 052026-ID621-SW1420-1.
35 | Med | Break date off | 820 | Beam Log 267 | 022426-ID443 beams (5-day) | Checklist scheduled 3/2; log broke them 3/1 (cast 2/24 + 5 days = 3/1). | Align the checklist date.
36 | Med | Break date off | 3426 | Cyl Log 2415 | 071526-Hut159-1 (28-day) | Checklist scheduled 8/2; cast 7/15 + 28 days = 8/12 (log correct). | Move checklist row to 8/12.
37 | Low | Tank conflict | 49-51 | Cyl Log 1605-1607 | 112625 sets (1/7) | Checklist says Tank A1 for all three; log says J8 / P3 / J8. | Align tank locations.
38 | Low | Tank conflict | 244-245 | Cyl Log 1726-1727 | S#4 CT675F25 / S#9 25153CM (1/21) | Checklist H6/H5 vs log H5/J8. | Align.
39 | Low | Tank conflict | 401 | Cyl Log 1697 | S#2_Mix#CT675F25 (2/2 hold) | Checklist N1 vs log M2. | Align.
40 | Low | Tank conflict (swapped pair) | 1212-1213 | Cyl Log 1833/1836 | 020926-ID421 & ID415 (3/23) | Checklist F/E vs log E/F — tanks appear swapped between the two sets. | Swap to match.
41 | Low | Tank conflict (swapped pair) | 2647-2648 | Beam Log 279-280 | 060426-ID653 & 060526-ID637 beams (6/12) | Checklist H5/J8 vs log S8/H5. | Align.
42 | Low | Tank conflict | 2912-2913 | Cyl Log 2210-2211 | Set #6/#7 Mix 2102-OPT-1 (6/30) | Checklist R4 vs log R3 (both sets). | Align.
43 | Low | Tank conflict | 2936 | Cyl Log 2216 | 052026-ID640-DS-1 (7/1) | Checklist S7 vs log S8. | Align.
44 | Low | Tank conflict | 3062 | Cyl Log 2247 | 052726-ID651-DS-1 (7/8) | Checklist S8 vs log Q6. | Align.
45 | Low | Tank conflict | 3358, 3607 | Cyl Log 2414-2415 | 071526-Hut159-1 (CTC) | Checklist says Tank E; log has the set in J7. | Align.
46 | Low | Tank conflict | 3547 | Cyl Log 2404 | 071026-Hut76-1 (CTC) | Checklist Tank E vs log M2. | Align.
47 | Low | Tank detail | 1028-1029, 1740-1742, 1065+ | Cyl Log var. | E-Top vs E / S4-5 vs S4-5 Top | Checklist and log differ in sub-position suffixes (Top/Bottom) on several sets. | Standardize tank naming (include Top/Bottom in both tabs).
48 | Low | Cosmetic | 1871 | Cyl Log 2119 | 042226-ID544-LCBEB105 | Checklist suffix -001 vs log -1; same set. | Standardize suffix convention.
49 | Low | Cosmetic | 3799 | Cyl Log 2417 | 71526-ID800-OS29_1-1 | Missing leading zero (071526) on the checklist. | Fix.

## Notes
Cross-check of 2026 SoCal CList vs Whittier Cylinder Log and Whittier Beam Log, plus dispatch (email request) descriptions embedded in the Job Description column.
Row numbers refer to actual Excel row numbers in each tab of 2026_SoCal_Checklist_Budget_Tracker_1.xlsx (checked 7/31/26).
Not flagged (verified as normal): cancelled 90-day holds absent from the checklist; conditional 56-day breaks never scheduled because the 42-day passed; January sets logged without dispatch IDs (ID naming started ~Feb); psi/annotation suffixes on checklist set numbers.
Invoice check: '105 Invoice July 26 (New)' Whittier Lab break lines match the SoCal CList exactly for every day in July (tests = specimens broken; ~0.5 hr per specimen; beams billed 1.5 hr / 3 beams). 7/31 breaks not yet entered on the invoice.